## Read me
MTWAFIQ Agile toolkit: the full method
Full method for agile and hybrid projects
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Not sure the project should be agile? Start with the Approach fit sheet: nine questions, two minutes.
Linked to problem solving: give every backlog item the Outcome ID it serves (Problem to outcome workbook).
The toolkit by stage
Stage | Sheet | Word templates
Vision and charter | Approach fit | Agile charter and roadmap
Product backlog | Product backlog | User stories, Ready and Done
Sprint planning and daily work | Team capacity | Sprint plan and review
Sprint board
Burndown
Blockers
Sprint review and release | Velocity | Sprint plan and review
Release plan
Retrospective | Improvement actions | Sprint retrospective
MTWAFIQ's own template for agile and hybrid projects, in line with PMI guidance. PMI, PMBOK, PMP and PMI-ACP are marks of the Project Management Institute, Inc., which does not endorse this template.

## Approach fit
Approach fit
Stage: Vision and charter
Two minutes, honest answers. 5 favours agile, 1 favours planning everything up front.
Area | Question | Your score (1-5) | 1 means | 5 means
Culture | Sponsor support for short cycles and changing scope |  | Wants every detail fixed up front | Backs it fully
Culture | Trust between the business and the team |  | Low: everything is checked | High
Culture | The team's freedom to decide how to do the work |  | Every step needs approval | The team decides
Team | Team size and focus |  | Over 30 people, mostly part time | 3 to 9 people, mostly full time
Team | Experience of the team in their roles |  | Mostly new | Mostly experienced
Team | Access to the business owner or the users |  | Once a month or less | Every day
Project | How likely the requirements are to change |  | Clear and stable | Likely to change often
Project | Can the result be delivered in small usable parts? |  | Only all at once | Yes, easily
Project | Cost of an early mistake |  | Severe: regulatory, safety or core system | Small and easy to fix
Area | Average | What it means
Culture
Team
Project
Overall
Result | Score all nine questions

## Product backlog
Product backlog
Stage: Product backlog
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Points not yet done |  | 8
ID | Epic | User story (As a…, I want…, so that…) | Acceptance criteria | Priority | Business value (1-10) | Story points | Value per point | Sprint | Status | Outcome ID
US-01 | Account opening | As a branch teller, I want the customer's ID data filled in for me, so that the account opens in one visit. | Given a valid national ID, when the teller scans it, then the fields are filled in and locked | Must | 9 | 5 | 1.8 | Sprint 1 | Ready | O-01
US-02 | Account opening | As a customer, I want an SMS when my account is open, so that I can use it at once. | Given an open account, when it is activated, then an SMS is sent within one minute | Should | 6 | 3 | 2 | Sprint 1 | New | O-01

## Team capacity
Team capacity
Stage: Sprint planning and daily work
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Team capacity (days) | 14.2 | Focus: the share of a day left for sprint work after meetings and support. Often 60% to 80%.
Member | Role | Working days in the sprint | Days off | Focus (%) | Capacity (days)
Member 1 | Business analyst | 10 | 1 | 80% | 7.2
Member 2 | Developer | 10 | 0 | 70% | 7

## Sprint board
Sprint board
Stage: Sprint planning and daily work
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Limit for In progress | 3 | In progress now | 1 | Points done | 0 | Points committed | 5
ID | Story or task | Owner | Story points | Status | Started | Finished | Cycle time (days)
US-01 | Pre-fill ID data at account opening | Member 2 | 5 | In progress | 2026-11-01

## Burndown
Burndown
Stage: Sprint planning and daily work
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Sprint length (working days) | 10 | Points committed | 40 | Enter the points still not done at the end of each day. Above the ideal line means behind.
Day | Ideal remaining | Actual remaining | Gap (above the line)
0 | 40 | 40 | 0
1 | 36 | 38 | 2
2 | 32 | 35 | 3
3 | 28 | 35 | 7
4 | 24
5 | 20
6 | 16
7 | 12
8 | 8
9 | 4
10 | 0
11 | 0
12 | 0
13 | 0
14 | 0
15 | 0
16 | 0
17 | 0
18 | 0
19 | 0
20 | 0

## Blockers
Blockers
Stage: Sprint planning and daily work
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
ID | Blocker | Raised by | Date raised | Effect on the sprint goal | Owner | Action | Cleared on | Days to clear
B01 | Test environment down for two days | Member 2 | 2026-11-01 | High | Scrum Master | Escalated to IT operations

## Velocity
Velocity
Stage: Sprint review and release
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Average velocity (last 3 sprints) | 32.7 | Points not yet done | 8 | Sprints left (forecast) | 1
Sprint | Committed points | Completed points | Completed (%) | Average of the last 3 | Sprint goal met?
Sprint 1 | 40 | 30 | 75% | 30 | No
Sprint 2 | 36 | 33 | 91.67% | 31.5 | Yes
Sprint 3 | 35 | 35 | 100% | 32.7 | Yes

## Release plan
Release plan
Stage: Sprint review and release
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Release | Target date | Main epics | Story points | Running total | Sprints needed from now | Status
Release 1 | Q1 | Account opening, e-KYC | 60 | 60 | 2 | Planned
Release 2 | Q2 | Cards, notifications | 80 | 140 | 5 | Planned

## Improvement actions
Improvement actions
Stage: Retrospective
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Sprint | Action | Owner | Due | Status | Did it help?
Sprint 1 | Refine the backlog every Tuesday | Product owner |  | Done | Yes: fewer surprises at planning