## Read me
MTWAFIQ project management toolkit: registers and logs
Organised by the PMI process groups and knowledge areas
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
The toolkit by process group
Process group | Sheet | Knowledge area | Word templates
Initiating | Stakeholders | Stakeholders | Business case, Project charter
Planning | Requirements RTM | Scope | Project management plan, Project scope statement
| WBS | Scope
| Schedule | Schedule
| Budget | Cost
| RACI | Resources
| Communications | Communications
| Risks | Risk
| Quality | Quality
Executing | Procurement | Procurement
| Issues | Integration
| Decisions | Integration
Monitoring and Controlling | Changes | Integration | Change request, Status report
| Earned value | Cost
Closing | Lessons learned | Integration | Project closure report
MTWAFIQ's own template, organised by the PMI process groups and knowledge areas. PMI, PMBOK and PMP are marks of the Project Management Institute, Inc., which does not endorse this template.

## Stakeholders
Stakeholders
Process group: Initiating · Knowledge area: Stakeholders
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
ID | Name | Role or department | Power (1-5) | Interest (1-5) | Strategy | Current engagement | Desired engagement | Owner
S01 | Head of Retail Operations | Retail Operations | 5 | 4 | Manage closely | Neutral | Supportive | Project manager

## Requirements RTM
Requirements RTM
Process group: Planning · Knowledge area: Scope
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
Req ID | Requirement | Source | Priority | Objective it serves | WBS item | Test or acceptance | Status
R01 | Account opening in one visit | Business case | Must | Objective 1 | 1.2 | UAT case 07 | Open

## WBS
WBS
Process group: Planning · Knowledge area: Scope
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
WBS code | Level | Work package | Deliverable | Description (WBS dictionary) | Owner | Effort (days) | Acceptance criteria
1.2 | 2 | Redesign the onboarding process | To-Be process map | As-Is and To-Be with KPIs | Process lead | 10 | Signed by the process owner

## Schedule
Schedule
Process group: Planning · Knowledge area: Schedule
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
Project start | 2026-11-01 | [8 empty] | Weeks from the project start
ID | Activity | WBS code | Owner | Start | Duration (days) | Finish | Predecessor | % complete | Status | 2026-11-01 | 2026-11-08 | 2026-11-15 | 2026-11-22 | 2026-11-29 | 2026-12-06 | 2026-12-13 | 2026-12-20 | 2026-12-27 | 2027-01-03 | 2027-01-10 | 2027-01-17
A01 | Map the As-Is process | 1.1 | Process lead | 2026-11-01 | 5 | 2026-11-05 |  | 40% | In progress

## Budget
Budget
Process group: Planning · Knowledge area: Cost
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
Total | 50000 | Contingency (%) | 10% | Total with contingency | 55000
Cost item | WBS code | Category | Quantity | Unit cost | Total | Funding source | Notes
Process consultant | 1.2 | People | 20 | 2500 | 50000 | Operations budget | Days

## RACI
RACI
Process group: Planning · Knowledge area: Resources
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
R responsible, A accountable (one per row), C consulted, I informed.
Activity or deliverable | Sponsor | Project manager | Business owner | Process lead | IT | Risk and compliance | Check
Approve the To-Be process | A | R | C | R | C | C | OK

## Communications
Communications
Process group: Planning · Knowledge area: Communications
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
Audience | Information needed | Channel | Frequency | Sender | Format | Feedback expected
Steering committee | Status, decisions needed | Meeting | Monthly | Project manager | Status report | Decisions

## Risks
Risks
Process group: Planning · Knowledge area: Risk
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
Risk ID | Risk (cause, event, effect) | Category | Probability (1-5) | Impact (1-5) | Score | Rating | Response (avoid, mitigate, transfer, accept) | Owner | Status
K01 | Core system change freeze delays the release, so go-live slips | Technology | 3 | 4 | 12 | Medium | Mitigate: book the release window now | IT lead | Open

## Quality
Quality
Process group: Planning · Knowledge area: Quality
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
Deliverable or process | Quality metric | Target | Actual | Met? | How measured | Owner
Account opening | First-time right (%) | 95% | 91% | No | Sample of 100 files a month | Quality lead

## Procurement
Procurement
Process group: Executing · Knowledge area: Procurement
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
Item or service | Make or buy | Contract type | Supplier | Value | Award date | Delivery date | Status
Process mining licence | Buy | Fixed price | Vendor A | 120000 |  |  | Tender

## Issues
Issues
Process group: Executing · Knowledge area: Integration
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
Issue ID | Issue | Raised by | Date raised | Priority | Owner | Action | Due | Status
I01 | Test environment not available | Test lead | 2026-11-01 | High | IT lead | Escalate to IT operations |  | Open

## Decisions
Decisions
Process group: Executing · Knowledge area: Integration
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
Decision ID | Decision | Options considered | Decided by | Date | Impact | Reference
D01 | Pilot in two branches first | All branches; two branches | Steering committee | 2026-11-01 | Lower risk, two weeks later | Minutes 03

## Changes
Changes
Process group: Monitoring and Controlling · Knowledge area: Integration
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
Change ID | Description | Requested by | Date | Scope impact | Schedule impact (days) | Cost impact | Decision | Decided by
C01 | Add e-signature to the new journey | Business owner | 2026-11-01 | Adds one deliverable | 10 | 45000 | Approved | Sponsor

## Earned value
Earned value
Process group: Monitoring and Controlling · Knowledge area: Cost
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
Budget at completion (BAC) | 500000 |  | CPI or SPI below 1: over cost or behind schedule. EAC = BAC / CPI.
Period | Planned value (PV) | Earned value (EV) | Actual cost (AC) | Cost variance (CV) | Schedule variance (SV) | CPI | SPI | EAC | ETC | VAC
Month 1 | 100000 | 90000 | 95000 | -5000 | -10000 | 0.94737 | 0.9 | 527777.7778 | 432777.7778 | -27777.7778

## Lessons learned
Lessons learned
Process group: Closing · Knowledge area: Integration
Blue cells are yours to fill in. Grey cells calculate by themselves. Row 6 is an example: replace it with your own.
ID | What happened | Effect | Lesson | Recommendation | Process group | Knowledge area | Owner
L01 | Test data arrived late | Testing slipped one week | Order test data with the environment | Add it to the schedule template | Planning | Schedule | Test lead