## Workflow
MTWAFIQ problem to outcome: the full method
Problem solving connected to project delivery
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
One set of IDs from start to end: P problem, RC root cause, S solution, C process change, D output, O outcome. Put the same IDs in the Agile backlog or the PMI WBS.
Step | What you do | Sheet | Gate | Gate status
1. Define the problem | Put a number on what is wrong, and a target. | Problems | The process owner agrees the problem and the number. | Passed
2. Find the root cause | Ask why until you reach something you can fix. | Root causes | Each root cause is checked with data, not opinion. | Passed
3. Choose the solution | Pick what removes the cause, and design the To-Be steps. | Solutions, Process changes, Outcomes | The sponsor approves the solutions and the outcome targets. | Passed
4. Deliver it as a project | Turn each solution into epics or work packages, then deliver in sprints or by plan. | Delivery link, Outputs | Every epic or work package names the solution and the outcome it serves. | Passed
5. Measure the outcome | Outputs are handed over; check that the number moved. | Outcome readings, Outcomes | The measure reached the target, or the gap has an action. | In progress
6. Keep the gain | The process owner checks the new way of working so it does not slip back. | Control plan, Traceability | The process owner runs the control plan, and the project closes. | In progress
Delivery: the epics or work packages go into the Agile toolkit (Product backlog, with the Outcome ID) or the PMI registers (WBS).
MTWAFIQ's own template. It links problem solving and process reengineering to the PMI and Agile toolkits, so every output serves a measured outcome.

## Problems
Problems
Steps: Define the problem
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Problem ID | Problem (what is wrong) | Process | Measure | Today | Target | By when | Process owner | Owner agreed? | Cost of doing nothing (per month) | Root causes checked
P-01 | Account opening takes 45 minutes and often two visits | Account opening | Minutes per account | 45 | 15 | Q2 | Head of Branch Operations | Yes | 120000 | 2

## Root causes
Root causes
Steps: Find the root cause
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Cause ID | Problem ID | Area | Root cause | Evidence (data) | Share of the problem (%) | Checked with data?
RC-01 | P-01 | Systems | ID data is typed by hand into two systems | 1 in 6 files has a typing error | 40% | Yes
RC-02 | P-01 | Policy and rules | Two signatures for every account, even low-risk ones | Policy review and 200 files | 30% | Yes

## Solutions
Solutions
Steps: Choose the solution
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Priority: impact 4-5 and effort 1-2 is a quick win; impact 4-5 and effort 3-5 is a major project; impact 1-3 and effort 1-2 is a fill-in; the rest, avoid.
Solution ID | Cause ID | Problem ID | Solution | Impact (1-5) | Effort (1-5) | Priority | Approved? | How we deliver it
S-01 | RC-01 | P-01 | Scan the ID once and send the data to both systems | 5 | 3 | Major project | Yes | Agile
S-02 | RC-02 | P-01 | One signature for low-risk accounts | 4 | 1 | Quick win | Yes | Just do it

## Process changes
Process changes
Steps: Choose the solution
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Minutes saved per account |  | 20
Change ID | Solution ID | As-Is step | Change | To-Be step | Minutes saved | Requirement or user story
C-01 | S-01 | Teller types the ID data into two systems | Automate | ID scanned once; the data reaches both systems | 12 | US-01
C-02 | S-02 | Supervisor signs every new account | Remove | Supervisor signs high-risk accounts only | 8 | Policy update

## Outcomes
Outcomes
Steps: Measure the outcome
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Progress works both ways: (before − latest) ÷ (before − target). 100% or more means the target is met.
Outcome ID | Problem ID | Outcome (what changes in the business) | Measure | Before | Target | Latest actual | Progress (%) | Met? | Outcome owner
O-01 | P-01 | Faster account opening | Minutes per account | 45 | 15 | 28 | 56.67% | No | Head of Branch Operations

## Outputs
Outputs
Steps: Deliver it as a project
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Output ID | Outcome ID | Output (what we deliver) | Solution ID | Due | Delivered on | Accepted by | Status
D-01 | O-01 | ID scanning live in all branches | S-01 | 2026-12-31 |  |  | In progress
D-02 | O-01 | New signing rule in force | S-02 | 2026-11-15 | 2026-11-13 | Head of Compliance | Delivered

## Delivery link
Delivery link
Steps: Deliver it as a project
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Epic or work package | Solution ID | Output ID | Outcome ID | How we deliver it | Owner | Sprint or date | Status | Linked?
Account opening: ID scanning | S-01 | D-01 | O-01 | Agile | Product owner | Sprints 1 to 3 | In progress | Yes

## Outcome readings
Outcome readings
Steps: Measure the outcome
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Outcome ID | Date | Actual | Comment
O-01 | 2026-11-01 | 45 | Before
O-01 | 2026-12-01 | 38 | New signing rule in force
O-01 | 2026-12-31 | 28 | ID scanning in 10 branches

## Control plan
Control plan
Steps: Keep the gain
Blue cells are yours to fill in. Grey cells calculate by themselves. The first rows are an example: replace them with your own.
Outcome ID | What we watch | Limit | How often | Who checks | If it goes over the limit | Handed to the process owner?
O-01 | Account opening time | Over 20 minutes on any day | Daily | Branch operations | Review the day's files and call the process owner | No

## Traceability
Traceability
Steps: Keep the gain
Fills itself from the other sheets: one line per outcome, from the problem to the control plan.
Outcome ID | Problem ID | Root causes checked | Solutions approved | Epics or work packages | Outputs delivered | Progress (%) | Met? | Control plan handed over?
O-01 | P-01 | 2 | 2 | 1 | 1 / 2 | 56.67% | No | No