## Tasks
Quick project tracker
Plan, then deliver
Blue cells are yours. Grey cells calculate by themselves. Replace the example rows with your own.
Project start | 2026-11-01 | Overall done | 20% | Tasks late | 0 |  | Weeks from the project start
Task | Owner | Start | Days | Finish | Status | Done (%) | 2026-11-01 | 2026-11-08 | 2026-11-15 | 2026-11-22 | 2026-11-29 | 2026-12-06 | 2026-12-13 | 2026-12-20 | 2026-12-27 | 2027-01-03 | 2027-01-10 | 2027-01-17
Map today's account opening steps | Process lead | 2026-11-01 | 5 | 2026-11-05 | On track | 60%
Agree the new steps with the branches | Business owner | 2026-11-08 | 10 | 2026-11-17 | Not started | 0%

## Risks and issues
Risks and issues
Plan, then deliver
Blue cells are yours. Grey cells calculate by themselves. Replace the example rows with your own.
Type | What could happen, or what happened | Owner | What we do | Due | Level | Status
Risk | Branch staff are not trained before go-live | Training lead | Book the training now |  | High | Open

## Weekly update
Weekly update
Plan, then deliver
Blue cells are yours. Grey cells calculate by themselves. Replace the example rows with your own.
Week of | Overall | Done this week | Next week | Help needed
2026-11-01 | Green | As-Is map 60% done | Finish the map, start the To-Be | None